## Execution-input
Id | Name | Test Suite | Test Case | Status | Assigned To | Tester | Planned Start Date | Planned End Date | Executed Start | Executed End | Requirements | Test Cycle
TR-13 | Open Facebook | TS-2 FaceBook Access | Open Facebook | Passed | Marc Solé | Anant Agarwal | 06/23/2026 | 06/26/2026 | 06/23/2026 12:43:21 PM | 06/23/2026 12:45:03 PM | RQ-8 Normal | CL-10 SIT
TR-14 | Login to facebook | TS-2 FaceBook Access | Login to facebook | Passed | Marc Solé | Anant Agarwal | 06/23/2026 | 06/26/2026 | 06/23/2026 12:45:29 PM | 06/23/2026 12:46:13 PM | RQ-8 Normal | CL-10 SIT
TR-16 | Look for profile | TS-7 Facebook working | Look for profile | Passed | David chidaine | Anant Agarwal | 06/23/2026 | 06/26/2026 | 06/23/2026 4:53:37 PM | 06/23/2026 4:53:46 PM | RQ-8 Normal | CL-10 SIT
TR-17 | Access web app | TS-7 Facebook working | Access web app | Passed | David chidaine | Anant Agarwal | 06/23/2026 | 06/26/2026 | 06/23/2026 4:54:12 PM | 06/23/2026 4:55:01 PM | RQ-8 Normal | CL-10 SIT
TR-23 | Like the post | TS-10 Facebook Functions | Like the post | Passed | David chidaine | Anant Agarwal | 06/25/2026 | 06/30/2026 | 06/25/2026 1:38:12 PM | 06/25/2026 1:39:02 PM | RQ-8 Normal | CL-10 SIT
TR-24 | Comments added | TS-10 Facebook Functions | Comments added | Passed | David chidaine | Anant Agarwal | 06/25/2026 | 06/30/2026 | 06/25/2026 1:39:34 PM | 06/25/2026 1:41:06 PM | RQ-8 Normal | CL-10 SIT
TR-25 | Logout | TS-10 Facebook Functions | Logout | Passed | David chidaine | Anant Agarwal | 06/25/2026 | 06/30/2026 | 06/25/2026 1:41:31 PM | 06/25/2026 1:42:10 PM | RQ-8 Normal | CL-10 SIT
TR-61 | Open Facebook | TS-3 FaceBook Access VPN | Open Facebook | Unexecuted | Olivier barriere |  | 06/25/2026 | 06/30/2026 |  |  | RQ-19 VPN | CL-10 SIT
TR-62 | Login to facebook | TS-3 FaceBook Access VPN | Login to facebook | Unexecuted | Olivier barriere |  | 06/25/2026 | 06/30/2026 |  |  | RQ-19 VPN | CL-10 SIT
TR-63 | Look for profile | TS-8 Facebook working VPN | Look for profile | Unexecuted | Olivier barriere |  | 06/25/2026 | 06/30/2026 |  |  | RQ-19 VPN | CL-10 SIT
TR-64 | Access web app | TS-8 Facebook working VPN | Access web app | Unexecuted | Olivier barriere |  | 06/25/2026 | 06/30/2026 |  |  | RQ-19 VPN | CL-10 SIT
TR-65 | Like the post | TS-11 Facebook Functions VPN | Like the post | Unexecuted | Olivier barriere |  | 06/25/2026 | 06/30/2026 |  |  | RQ-19 VPN | CL-10 SIT
TR-66 | Comments added | TS-11 Facebook Functions VPN | Comments added | Passed | Olivier barriere | Olivier barriere | 06/25/2026 | 06/30/2026 | 06/25/2026 1:45:38 PM | 06/25/2026 1:46:39 PM | RQ-19 VPN | CL-10 SIT
TR-67 | Logout | TS-11 Facebook Functions VPN | Logout | Passed | Olivier barriere | Olivier barriere | 06/25/2026 | 06/30/2026 | 06/25/2026 12:59:45 PM | 06/25/2026 12:59:49 PM | RQ-19 VPN | CL-10 SIT
TR-68 | Open Facebook | TS-4 FaceBook Access Accenture VPN | Open Facebook | Passed | Olivier barriere | Olivier barriere | 06/25/2026 | 06/30/2026 | 06/25/2026 1:00:53 PM | 06/25/2026 1:01:42 PM | RQ-25 Accenture VPN | CL-10 SIT
TR-69 | Login to facebook | TS-4 FaceBook Access Accenture VPN | Login to facebook | Unexecuted | Olivier barriere |  | 06/25/2026 | 06/30/2026 |  |  | RQ-25 Accenture VPN | CL-10 SIT
TR-70 | Look for profile | TS-9 Facebook working Accenture VPN | Look for profile | Unexecuted | Olivier barriere |  | 06/25/2026 | 06/30/2026 |  |  | RQ-25 Accenture VPN | CL-10 SIT
TR-71 | Access web app | TS-9 Facebook working Accenture VPN | Access web app | Unexecuted | Olivier barriere |  | 06/25/2026 | 06/30/2026 |  |  | RQ-25 Accenture VPN | CL-10 SIT
TR-72 | Like the post | TS-12 Facebook Functions Accenture VPN | Like the post | Unexecuted | Olivier barriere |  | 07/01/2026 | 07/06/2026 |  |  | RQ-25 Accenture VPN | CL-10 SIT
TR-73 | Comments added | TS-12 Facebook Functions Accenture VPN | Comments added | Unexecuted | Olivier barriere |  | 07/01/2026 | 07/06/2026 |  |  | RQ-25 Accenture VPN | CL-10 SIT
TR-74 | Logout | TS-12 Facebook Functions Accenture VPN | Logout | Unexecuted | Olivier barriere |  | 07/01/2026 | 07/06/2026 |  |  | RQ-25 Accenture VPN | CL-10 SIT
TR-75 | Open Facebook | TS-5 FaceBook Access VDI | Open Facebook | Failed | Olivier barriere |  | 07/01/2026 | 07/06/2026 |  |  | RQ-30 VDI | CL-10 SIT
TR-76 | Login to facebook | TS-5 FaceBook Access VDI | Login to facebook | Blocked | Olivier barriere |  | 07/01/2026 | 07/06/2026 |  |  | RQ-30 VDI | CL-10 SIT
TR-77 | Look for profile | TS-13 Facebook working VDI | Look for profile | Blocked | Stephane duong | Akshay Salgaonkar | 06/24/2026 | 06/29/2026 | 06/24/2026 10:19:54 PM | 06/24/2026 10:25:33 PM | RQ-30 VDI | CL-10 SIT
TR-78 | Access web app | TS-13 Facebook working VDI | Access web app | Blocked | Stephane duong |  | 06/24/2026 | 06/29/2026 |  |  | RQ-30 VDI | CL-10 SIT
TR-79 | Like the post | TS-14 Facebook Functions VDI | Like the post | Blocked | Patricia Van.Helvert |  | 06/25/2026 | 06/30/2026 |  |  | RQ-30 VDI | CL-10 SIT
TR-80 | Comments added | TS-14 Facebook Functions VDI | Comments added | Blocked | Stephane duong |  | 06/25/2026 | 06/30/2026 |  |  | RQ-30 VDI | CL-10 SIT
TR-81 | Logout | TS-14 Facebook Functions VDI | Logout | Blocked | Stephane duong |  | 06/25/2026 | 06/30/2026 |  |  | RQ-30 VDI | CL-10 SIT
TR-83 | Waste of time | TS-15 waste of time | Waste of time | Blocked | Olivier barriere |  | 07/01/2026 | 07/06/2026 |  |  | RQ-31 waste of time | CL-10 SIT

## Defects-INPUT
Id | Summary | Module | Assigned To | Submitter | Severity | Status | Priority | Submitted Date | Closed Date | Target Date | Root Cause | Defect Type | Workstream
DF-26 | Unable to access Facebook login | MD-82 Facebook Access | Akshay Salgaonkar | Akshay Salgaonkar | High | In Progress | Medium | 06/24/2026 10:25:17 PM | 06/24/2026 11:00:00 PM |  | Security | Security | Facebook
DF-27 | Incorrect user name password | MD-89 Facebook Access VPN | Olivier barriere | Olivier barriere | Medium | In Progress | High | 06/25/2026 1:33:05 PM | 06/25/2026 8:30:00 PM | 06/28/2026 | Security | Security | Facebook
DF-29 | No logout symbol | MD-68 Facebook Functions Accenture VPN |  | Adwait Nadkarni | Medium | Closed | Medium | 06/25/2026 3:33:06 PM | 06/25/2026 3:39:00 PM |  | Security | Security | Facebook